## Project Planner
Project Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
Feature | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS: in half days starting fromfirst half of 11/17/2021
[6 empty] | Wed |  | Thurs |  | Fri |  | Sat |  | Sun |  | Mon |  | Tues |  | 24th |  | Thurs |  | Fri |  | Sat |  | Sun |  | Mon |  | Tues |  | 1st |  | Thurs |  | Fri |  | Sat |  | Sun |  | Mon |  | Tues |  | 8th |  | Thurs |  | Fri |  | Sat |  | Sun |  | Mon |  | Tues |  | Wed |  | Thurs |  | Fri | Sat | Sun | Mon | Tues
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Sign in | 1 | 4 | 1 | 3 | 100%
Sign up | 1 | 4 | 1 | 4 | 90%
Logout Account | 1 | 4 | 1 | 4 | 90%
Delete Account Option | 4 | 4 | 5 | 2 | 100%
Update Account Option | 4 | 2 | 5 | 2 | 100%
ToDo List | 7 | 2 | 7 | 20 | 100%
Home page Navigation | 1 | 14 | 2 |  | 70%
Upload markdown file | 6 | 4 | 6 | 5 | 90%
render markdown file | 9 | 5 | 9 | 10 | 100%
Create Flash cards with markdown rendering (preview) | 18 | 4 | 18 | 8 | 100%
Share notes | 17 | 6 | 17 |  | 0%
Create pomodoro timer | 21 | 8 | 23 |  | 50%
Share flashcards | 27 | 4 |  |  | 0%
Create timeblocks | 28 | 8 |  |  | 0%
Fill notes with imported md file | 27 | 4
Visualize timeblocks | 25 | 11 |  |  | 0%
Make Visually appealing | 27 | 11 | 1 |  | 10%
Feature 15
Feature 16
Feature 17
Feature 18
Feature 19
Feature 20
Feature 21
Feature 22
Feature 23
Feature 24
Feature 25
Feature 26